## Summary
Island Club 4
Special Assessment Expense Summary
May 17, 2024
Category of Spend | Budgeted In Assessment | Work Awarded / Committed | Amount Paid to Date | Amount In Process and Remaining to Pay
Mansards, Flat Roofs and Contingency | 1480000 | 1450000 | 1410783.17 | 39216.83
Sewers | 600960 | 628460 | 592671.76 | 35788.24
Waterpipes (5 Buildings) | 107937.22 | 82086.27 | 69098.93 | 12987.34
Fire Alarms (5 Buildings) | 52975 | 43647.19 | 43647.19 | 0
Engineering Report for 50 Year Certification | 23500 | 0 | 0 | 0
Security Cameras & Video Back-up | 66700 | 69700 | 60200 | 9500
Concrete Restoration and Contingency | 205000 | 157326.48 | 111822.48 | 45504
Termite Removal all Storage Areas (5 Buildings) | 131342 | 170750 | 145750 | 25000
Painting (5 Buildings) | 210135 | 0 | 0 | 0
Landscape Architect, Sprinklers,Walkways, Landscaping & Ashphalt | 75000 | 41804.41 | 31880.42 | 9923.99
Other | 0 | 77440.88 | 76190.88 | 1250
| 2953549.22 | 2721215.23 | 2542044.83 | 179170.4 | 411504.39
Remaining Budget yet to be Commited with Vendors | 232333.99
155.4
Note : Categories that require further discussion and planning in yellow. |  |  |  |  | 273.6
429

## Details
Island Club 4
Special Assessment Expense Analysis
May 17, 2024
Category of Spend | [5 empty] | Budgeted In Assessment |  |  | Contract / Invoice Amount |  |  |  | Payments to Date |  | Account |  | Work in Process / |  |  | SA | Reserve | Operating
Payment Remaining
Mansards, Flat Roofs and Contingency | [5 empty] | 1480000
|  | JW Jones Contracting |  |  |  |  | (Roofing for K,L,M,N,O) |  | 1450000 |  |  |  | 11/29 | 191000 | SA | 1015
[13 empty] | 1/5/24 | 209000 | SA | 1031 |  |  |  | 209000
[13 empty] | 2/1/24 | 185000 | SA | 1040 |  |  |  | 185000
[13 empty] | 2/27/24 | 25000 | SA | 1048 |  |  |  | 25000
[13 empty] | 2/27/24 | 155000 | SA | 1047 |  |  |  | 155000
[12 empty] | (Hatches) | 3/11/24 | 5783.17 | SA | 1051 |  |  |  | 5783.17
[13 empty] | 3/19/24 | 250000 | SA | 1055 |  |  |  | 250000
[13 empty] | 4/2/2024 | 25000 | SA | 1061 |  |  |  | 25000
[13 empty] | 4/2/2024 | 200000 | SA | 1062 |  |  |  | 200000
[13 empty] | 5/1/24 | 100000 | SA | 1068 |  |  |  | 100000
[13 empty] | 5/6/24 | 50000 | SA | 1070 |  |  |  | 50000
[13 empty] | 5/6/24 | 15000 | SA | 1071 |  |  |  | 15000
Budget Remaining Not Committed / (Overspend) |  |  |  |  | 30000 | [8 empty] | 1410783.17 |  |  |  | 39216.83
Sewers | [5 empty] | 600960
|  | Cast Iron Plumbing & Drainage | [5 empty] | Bldg K | 89472 |  |  |  | 10/2/23 | 35000 | Reserve | 10001 |  |  |  |  | 35000
[8 empty] | Bldg L | 74496 |  |  |  | 11/13/23 | 20132 | SA | 1010 |  |  |  | 20132
[8 empty] | Bldg M | 75264 |  |  |  | 11/29/2023 | 125000 | SA | 1014 |  |  |  | 125000
[8 empty] | Bldg N | 207744 |  |  |  | 12/14/23 | 40818 | SA | Bank Check |  |  |  | 40818
[8 empty] | Bldg O | 153984 |  |  |  | 1/19/24 | 20686 | SA | 1035 |  |  |  | 20686
[9 empty] | 600960 |  |  |  | 2/1/24 | 6000 | SA | 1041 |  |  |  | 6000
[13 empty] | 2/5/24 | 92390.46 | SA | 1042 |  |  |  | 92390.46
[6 empty] | Extras | [6 empty] | 2/14/24 | 41372 | SA | 1045 |  |  |  | 41372
[6 empty] | (pipes M&N Storage Rooms) |  |  | 1000 |  |  |  | 2/21/24 | 1000 | Oper | 1241241 | [5 empty] | 1000
[13 empty] | 3/11/24 | 30796.8 | SA | 1050 |  |  |  | 30796.8
[13 empty] | 4/1/24 | 30796.8 | SA | 1059 |  |  |  | 30796.8
[6 empty] | Extras O Bldg |  |  | 2500 |  |  |  | 4/1/24 | 2500 | SA | 1058 |  |  |  | 2500
[6 empty] | Extras O Bldg |  |  | 8000 |  |  |  | 4/1/24 | 8000 | SA | 1057 |  | (Not Cashed) ? |  | 8000
[6 empty] | O107 Condensation Line |  |  | 4000 |  |  |  | 4/1/2024 | 4000 | SA | 1060 |  |  |  | 4000
[6 empty] | N Bldg Emergency Repair |  |  | 12000 |  |  |  | 1/23/24 | 6000 | SA | 1036 |  |  |  | 6000
[6 empty] | Sub-total Extras |  |  | 27500 |  |  |  | 4/5/24 | 44698.1 |  | 1064 |  |  |  | 44698.1
[13 empty] | 4/24/24 | 29798.4 |  | 1066 |  |  |  | 29798.4
[13 empty] | 5/1/24 | 53683.2 |  | 1067 |  |  |  | 53683.2
[9 empty] | 628460 |  |  |  |  | 592671.76 |  |  |  | 35788.24
Budget Remaining Not Committed / (Overspend) |  |  |  |  | -27500
Waterpipes (5 Buildings) | (5 Buildings) |  |  |  |  | 107937.22
|  | Mainline Plumbing | [8 empty] | (Inspections) |  | 10/3/23 | 12000 | Reserve | [5 empty] | 12000
|  | Water Main replacement | [5 empty] | Bldg K | 11395 |  |  |  | 11/15/23 | 12000 | SA | 1012 |  |  |  | 12000
[8 empty] | Bldg N | 24615.55 |  |  |  | 10/3/2023 | 382.56 |  | (Missing Cant Find?) |  |  |  | 382.56
[8 empty] | Bldg L | 11037.86 |  |  |  | 12/15/23 | 3617.44 | SA | 1023 |  |  |  | 3617.44
[8 empty] | Bldg M | 11037.86 |  |  |  | 12/18/23 | 9846.22 | SA | 1027 |  |  |  | 9846.22
|  |  | Additional work (5 shut off valves) | [5 empty] | 4000 |  |  |  | 3/15/24 | 6837.57 | SA | 1054 |  |  |  | 6837.57
[13 empty] | 5/13/24 | 4415.14 | SA | 1073 |  |  |  | 4415.14
[9 empty] | 62086.27 |  |  |  |  | 49098.93 |  |  |  | 12987.34
|  | Beneath Your Feet Plumbing | [6 empty] | 22000 | O Bldg Water Pipe |  | (On Account) | 10/11/23 | 5000 | Oper | 1061
|  | (Contract Amount Not Clear, Just Invoices and they don't match contract) | [6 empty] | 8000 | O Bldg Extras |  | Balance | 11/3/23 | 15000 | SA | 1006 | [5 empty] | 5000
|  | (Contract $30k and Payments $20K) | [6 empty] | -10000 | Our Adjustment | [9 empty] | 15000
[9 empty] | 20000 |  |  |  |  | 20000 | (Marked Paid in Full) |  |  | 0
Budget Remaining Not Committed / (Overspend) |  |  |  |  | 25850.95 |  |  |  | 82086.27 |  |  |  |  | 69098.93 |  |  |  | 12987.34 | 12987.34
Fire Alarms (5 Buildings) | [5 empty] | 52975
ADT
|  | Contract and Invoices don’t match? | [5 empty] | Bldg O | 13512
|  | 52975 | [5 empty] | Bldg K&L | 9376
[8 empty] | Bldg M | 11980
[8 empty] | Bldg N | 12987
[9 empty] | -4207.81 | (No Documentation of this Adjustment)
[9 empty] | 43647.19 | 43647.19 | (Paid in Full) |  | 11/30/23 | 43647.19 |  |  |  | 0 |  | 43647.19
Budget Remaining Not Committed / (Overspend) |  |  |  |  | 9327.81 |  |  |  | 0
Engineering Report for 50 Year Certification | [5 empty] | 23500
(No record of Contract or Payment yet. Have we done an Engineering Report?)
Budget Remaining Not Committed / (Overspend) |  |  |  |  | 23500
Security Cameras & Video Back-up | [5 empty] | 66700
|  | Max-Q Inc. |  | (DVR and Camera) |  | 66700 |  | Bldg L | 10800 |  |  |  | 10/2/23 | 8750 | Oper | 1049 | [5 empty] | 8750
|  | (No Contract Just Invoices) | [5 empty] | Bldg M | 16800 |  |  |  | 10/20/23 | 3000 | Oper | 1068 | [5 empty] | 3000
[8 empty] | Bldg O | 17500 |  |  |  | 11/14/23 | 5000 | SA | 1011 |  |  |  | 5000
(Invoices confusing, numbers adjusted. No K Bldg Invoice?) | [7 empty] | Bldg N | 16800 |  |  |  | 11/30/23 | 10000 | SA | 1017 |  |  |  | 10000
[9 empty] | 61900 |  |  |  | 1/25/24 | 16650 | SA | 1038 |  |  |  | 16650
[8 empty] | Pending ? | 4800 |  |  |  | 2/14/24 | 3000 | SA | 1046 |  |  |  | 3000
|  | Storage Rooms Added |  |  |  | 3000 |  |  | 3000 |  |  |  | 3/7/24 | 5400 | Oper | 1275 | [5 empty] | 5400
[13 empty] | 3/7/24 | 8400 | Oper | 1276 | [5 empty] | 8400
69700
[9 empty] | 69700 |  |  |  |  | 60200 |  |  |  | 9500
Budget Remaining Not Committed / (Overspend) |  |  |  |  | -3000
Concrete Restoration and Contingency | [5 empty] | 205000
|  | Engineer | [6 empty] | 1500 |  |  |  | 2023-12-12 | 1000 | SA | 1212 |  |  |  | 1000
[13 empty] | 2024-01-18 | 500 | Oper | 1169 | [5 empty] | 500
[14 empty] | 1500 |  |  |  | 0
|  | Robmar | [6 empty] | 55826.48 |  |  |  | 11/16/2023 | 10000 | SA | 1013 |  | (Not Cashed)? |  | 10000
[13 empty] | 11/30/2023 | 15000 | SA | 1019
[13 empty] | 1/18/2024 | 25243.83 | SA | 1033 |  |  |  | 15000
[14 empty] | 50243.83 | [5 empty] | 25243.83
[13 empty] | 2/8/24 | 5582.65 | SA | 1044 |  |  |  | 5582.65
[14 empty] | 55826.48 |  |  |  | 0
|  | JW Jones Contracting (Concrete Restoration Bldgs K,L,M,N,O) | [6 empty] | 100000 |  |  |  | 1/10/24 | 25000 | SA | 1032
[13 empty] | 2/27/24 | 25000 | SA | 1048 |  |  |  | 25000
[13 empty] | 2/27/24 | 1656 | Oper | 1250 |  |  |  | 25000
[10 empty] | (Should this be Operating) |  | (Repairs) | 3/11/24 | 1390 | SA | 1057 | [5 empty] | 1656
[12 empty] | (Repairs) | 3/11/24 | 1450 | SA | 1052 |  |  |  | 1390
[14 empty] | 54496 |  |  |  | 45504 |  | 1450
Budget Remaining Not Committed / (Overspend) |  |  |  |  | 47673.52 |  |  |  | 157326.48 |  |  |  |  | 111822.48 |  |  |  | 45504
Termite Removal all Storage Areas (5 Buildings) | [5 empty] | 131342
|  | American Door | [6 empty] | 50000 |  |  |  | 1/5/24 | 25000 | SA | 1029 |  | 25000 |  | 25000
Laundry Storage & Office Doors (Fiberglass w/ Frames)
|  | Atlantic Rack |  | (No Contract Found) |  |  |  |  | 120750 | (Storage Room Racks) |  |  | 12/15/23 | 60000 | SA | 1022 |  | 0 |  | 60000
[13 empty] | 3/27/24 | 60750 | SA | 1056 |  |  |  | 60750
[9 empty] | 170750 |  |  |  |  | 145750 |  |  |  | 25000
Budget Remaining Not Committed / (Overspend) |  |  |  |  | -39408
Painting (5 Buildings) | [5 empty] | 210135
0
Budget Remaining Not Committed / (Overspend) |  |  |  |  | 210135
Landscape Architect, Sprinklers,Walkways, Landscaping & Ashphalt | [5 empty] | 75000
|  | (Landscape Architect Plan) |  |  | Tom White |  |  |  | 2900 | Site Work
[9 empty] | 3400 | Design Phase
[9 empty] | 6300 | (Extras are $150 per hour) |  |  | 1/5/24 | 3000 | (Deposit) |  |  | 3300 |  | 3000
|  | Absolute Ashphalt | [6 empty] | 14618.81 | (Repair Sewer Damage |  |  | 3/5/24 | 7309.41 | Oper | 1269 | [5 empty] | 7309.41
[10 empty] | Replace 30 Car Stops) |  |  | 3/13/24 | 7309.4 | Oper | 1295 |  | 0 |  |  |  | 7309.4
[9 empty] | 10245.6 | (Replace 29 Parking Stall |  |  | 2/5/2024 | 5122.8 | SA | 1043 |  | 1873.99 |  | 5122.8
[10 empty] | and Stops) |  |  | 4/10/24 | 3248.81
8371.61
[9 empty] | 1140 | (19 Damaged Car Stops) |  |  | 2/5/2024 | 1140 | SA | 1043 |  | 0 |  | 1140
[9 empty] | 26004.41 |  |  |  |  | 24130.42 |  |  |  | 1873.99 | 1873.99
|  | IESG - Paver Installation | [6 empty] | 9500 | (Walkways) |  |  | 5/2/24 | 4750 | SA |  |  | 4750
(No Contract just Estimate)
Budget Remaining Not Committed / (Overspend) |  |  |  |  | 33195.59 |  |  |  | 41804.41 |  |  |  |  | 31880.42 |  |  |  | 9923.99 | 9923.99
Other Expenses Not Budgeted |  |  |  |  | 0
|  | Atlantic Electric | [6 empty] | 1250 | Laundry Room Wiring Repairs | [7 empty] | 1250
[9 empty] | 9400 | Storage Room Lighting |  |  | 3/8/24 | 9400 | 1049
10650
|  | Pye-Barker Fire Safety | [6 empty] | 4895.88 | (Fire Extinguishes) |  |  | 11/7/23 | 4895.88 | SA | 1007 |  | 0 |  | 4895.88
(Paid out of SA, should we move to HOA and Operating?)
Sterling Construction
[9 empty] | 15945 | 23 Laundry Room Windows |  |  | 10/5/23 | 2500 | Res | 1004 |  |  |  |  | 2500
[13 empty] | 11/13/23 | 2500 | SA | 1009 |  |  |  | 2500
[13 empty] | 11/30/23 | 2500 | SA | 1018 |  |  |  | 2500
[13 empty] | 12/14/23 | 8445 | SA | Bank Check |  |  |  | 8445
[14 empty] | 15945 |  |  |  | 0
[9 empty] | 12000 | 12 Storage Room Windows |  |  | 1/4/24 | 6000 | SA | 1030 |  |  |  | 6000
[13 empty] | 2/20/24 | 6000 | Oper | 1239 | [5 empty] | 6000
[14 empty] | 12000 |  |  |  | 0
[9 empty] | 27945 |  |  |  |  | 27945 |  |  |  | 0
|  | All Services Elevator |  |  | Deficiency Report |  |  |  | 1000 |  |  | (Deposit) | 10/11/23 | 12000 | Reserve | 1005 |  |  |  |  | 12000
[13 empty] | 9/12/23 | 1000 | Oper | 1026 | [5 empty] | 1000
[5 empty] | Inspection and Repairs |  |  |  | 23850 |  |  |  | 12/8/2023 | 4000 | Reserve | 1006 |  |  |  |  | 4000
[13 empty] | 12/8/2023 | 7850 | SA | 1020 |  |  |  | 7850
[9 empty] | 24850 |  |  |  |  | 24850
|  | Empire (Landscaping?) | [6 empty] | No Details |  |  |  | 12/15 | 3500 | SA | 1025
[13 empty] | 12/15 | 2100 | SA | 1024
[9 empty] | 5600 |  |  |  |  | 5600
|  | Joe Dobes Electric | [6 empty] | 3500 | Deposit on Laundry Room AC |  |  | 12/18 | 3500 | SA | 1026
Budget Remaining Not Committed / (Overspend) |  |  |  |  | -77440.88 |  |  |  | 77440.88 |  |  |  |  | 76190.88 |  |  |  | 1250 | 1250
Grand Total | [5 empty] | 2953549.22 |  |  | 2721215.23 |  |  |  |  | 2542044.83 |  |  |  | 179170.4 | 179170.4 | 2203721.21 | 65500 | 55324.81
[6 empty] | Total Special |  |  | Amount Identifed / |  |  |  |  | Amount Paid |  |  |  | Balance to |  | 2324546.02
[6 empty] | Assessment Budget |  |  | Committed |  |  |  |  | To Date |  |  |  | be Paid